## Risk Register
Cybersecurity risk register
Northstar Client Services — fictional training case, 26 Oct 2026
Risks identified | 5 |  | Risks scored | 1 |  | High or critical | 1
Risk ID | Asset / process | Risk statement | Assumed control gap | Likelihood (1–5) | Impact (1–5) | Inherent score | Inherent rating | NIST CSF 2.0 | Response | Recommended control actions | Owner (role) | Evidence to request | Assessment status | Target date
GRC-001 | Microsoft 365 identities | Stolen employee passwords could allow attackers to access client files. | Multi-factor authentication (MFA) is assumed to be missing for some accounts. | 4 | 5 | 20 | Critical | PR.AA-03 | Mitigate | Enforce MFA for all users; prioritize admins; verify policy with sign-in logs. | IT Manager | MFA settings, enrollment report, sign-in logs | Draft / hypothetical
GRC-002 | Cloud backup and recovery | A ransomware incident could cause prolonged downtime if backups cannot be restored. | Recovery tests are assumed to be absent or outdated. |  |  |  | Not assessed | PR.DS-11 | Mitigate | Schedule restore tests, monitor backup failures, and keep test evidence. | IT Manager | Backup policy, restore test records, backup job alerts | Pending assessment
GRC-003 | Windows endpoints | An attacker could exploit unpatched software and compromise workstations. | Security patches are assumed to be applied late on some laptops. |  |  |  | Not assessed | PR.PS-02 | Mitigate | Document patch deadlines, monitor update compliance, and remediate exceptions. | Endpoint Administrator | Patch dashboard, device inventory, exception list | Pending assessment
GRC-004 | Shared client documents | Excessive access permissions could expose confidential client information. | Shared folders are assumed to give broad access beyond job needs. |  |  |  | Not assessed | PR.AA-05 | Mitigate | Review shared-file permissions, remove unnecessary access, and set periodic reviews. | Data Owner | Permission exports, access review sign-off, policy | Pending assessment
GRC-005 | Employee phishing awareness | A phishing email could trick staff into giving up passwords or opening malware. | Security-awareness training is assumed to be inconsistent. |  |  |  | Not assessed | PR.AT-01 | Mitigate | Assign annual training and targeted refreshers; track completion and follow-up. | Security Lead | Training completion records, awareness plan | Pending assessment

## Scoring Guide
Risk scoring guide
Project-defined illustrative scales; NIST CSF 2.0 does not prescribe this formula.
Likelihood score | Illustrative definition | Impact score | Illustrative definition
1 | Rare: not expected in normal conditions | 1 | Negligible: minimal disruption or loss
2 | Unlikely: possible but infrequent | 2 | Minor: limited operational effects
3 | Possible: plausible occurrence | 3 | Moderate: meaningful disruption or cost
4 | Likely: elevated probability | 4 | Major: serious service or data impact
5 | Very likely: frequent or expected | 5 | Severe: sustained outage or sensitive-data exposure
Inherent risk score = likelihood × impact (before improvements)
Rating | Score range
Low | 1–4
Moderate | 5–9
High | 10–16
Critical | 17–25
Only GRC-001 is scored as a worked example. Other risks await assessment.
Do not treat hypothetical gaps as verified control failures or completed audit findings.
Framework reference | https://nvlpubs.nist.gov/nistpubs/CSWP/NIST.CSWP.29.pdf